## Product Backlog
CoachAI - Product Backlog (AI Customer Support Assistant with Live Response Guidance)
Project: Development of AI-Powered Customer Support Assistant with Live Response Guidance ¦ Batch: Jun-Aug 2026 ¦ Team: MasterJi27 + CoachAI Team ¦ Repo: github.com/MasterJi27 ¦ Sprints: 6 (6 weeks) ¦ Deadline: 28-Aug-2026
Planned Sprint | Actual Sprint | US ID | User Story / Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-001 | As a stakeholder, I want project charter and requirement analysis covering problem (late coaching, scattered KB, late escalation) and solution (real-time copilot) so scope is clear | MUST HAVE | No Dependency | Team Lead / BA | 3- Completed
1 | 1 | US-002 | As a developer, I want GitHub repo with branching, .gitignore, MIT license and README skeleton so collaboration is enabled | MUST HAVE | US-001 | Team Lead | 3- Completed
1 | 1 | US-003 | As an architect, I want system architecture (React + Node + Python + Postgres + LLM chain Azure -> OpenRouter -> Groq) and 9-step per-turn flow documented | MUST HAVE | US-001 | AI Architect | 3- Completed
1 | 1 | US-004 | As DevOps, I want env config (.env.example, DATABASE_URL, AZURE/GROQ/OPENROUTER keys, COMPOSIO keys) with graceful degradation if keys missing | MUST HAVE | US-002 | Backend Team | 3- Completed
1 | 1 | US-005 | As PM, I want Orchestrator and ConversationManager session lifecycle (start/process/advance/end + rehydration via full_state JSON) for serverless | MUST HAVE | US-003 | AI Team | 3- Completed
2 | 2 | US-006 | As agent, I want Customer Simulator (LLM temp 0.8, Hinglish <=140 chars, sentiment state machine, 6 fallbacks) for realistic training | MUST HAVE | US-005 | AI Team | 3- Completed
2 | 2 | US-007 | As agent, I want Intent and Sentiment Agent (intent + frustration 0-1 + trend -1..1, JSON regex fallback) in <0.5s | MUST HAVE | US-005 | AI Team | 3- Completed
2 | 2 | US-008 | As manager, I want Escalation Monitor (weighted: frustration*0.4 + sentiment*0.2 + trend*0.15 + keywords*0.1 + length*0.1 + repetition*0.05) | MUST HAVE | US-007 | AI Team | 3- Completed
2 | 2 | US-009 | As agent, I want Coaching Suggestion (suggested reply + tone/clarity 1-5 + macros library + retention STAY15) before send | MUST HAVE | US-007 | AI Team | 3- Completed
2 | 2 | US-010 | As QA, I want Post-Interaction Summary (overall = resolution*0.5 + coaching*0.3 + clarity*0.2) and PerformanceReport | MUST HAVE | US-009 | AI Team | 3- Completed
3 | 3 | US-011 | As KB admin, I want RAG ingestion (.txt/.pdf/.docx/.json/.md/.csv/.html) with paragraph -> 512-char chunks and sentence re-split | MUST HAVE | US-001 | AI Team | 3- Completed
3 | 3 | US-012 | As agent, I want hybrid retrieval: semantic (OpenRouter nemotron 2048d cosine, JSONB cache) + BM25/keyword offline fallback | MUST HAVE | US-011 | AI Team | 3- Completed
3 | 3 | US-013 | As agent, I want Knowledge Recommendation (agentic RAG 1 tip) + KB-gap <0.45 -> pending FAQ draft via Auto-KB | MUST HAVE | US-012 | AI Team | 3- Completed
3 | 3 | US-014 | As manager, I want Deep Analysis (1 LLM call -> CSAT 1-5, churn %, viral/PR + statement, fraud+protocol, defection+offer, mind-read) | SHOULD HAVE | US-007 | AI Team | 3- Completed
3 | 3 | US-015 | As analyst, I want Predictive CSAT, Defection (swiggy/zepto keywords), Viral Threat, Fraud Detector agents | SHOULD HAVE | US-014 | AI Team | 3- Completed
4 | 4 | US-016 | As agent, I want Mind Reader, Multiverse (2-3 what-if branches + CSAT), Cognitive Load, Patience Clock, Bot Agent (Zomato menu, escalate on human/frustration>=0.7) | SHOULD HAVE | US-014 | AI Team | 3- Completed
4 | 4 | US-017 | As agent, I want Manager Supervisor (whisper/takeover if >=0.5), Compliance Monitor, Tone Rewriter (<10 chars -> canned apology), Auto-Pilot (one-click refund/voucher) | SHOULD HAVE | US-009 | AI Team | 3- Completed
4 | 4 | US-018 | As manager, I want Jira Generator (transcript -> ticket), Scenario Generator, QA Audit (21 checks, pass if overall>=0.75) | SHOULD HAVE | US-010 | AI Team | 3- Completed
4 | 4 | US-019 | As integrator, I want Composio (JIRA_CREATE_ISSUE, GMAIL, Slack) + mock_backend (refund Rs.500 guard, voucher) with graceful fail | COULD HAVE | US-018 | Backend Team | 3- Completed
4 | 4 | US-020 | As trainee, I want Survival Mode (4 tickets, grading 0.85/0.6/0.35, HP/streak/power-ups +500) and Hall of Fame/Shame (>=0.85 / <=0.45) | COULD HAVE | US-010 | AI Team | 3- Completed
5 | 5 | US-021 | As user, I want Node Express backend (auth register/login/guest/me, sessionStore pg rehydration, 40+ routes, rag BM25, llm chain) port 8000 | MUST HAVE | US-005 | Backend Team | 3- Completed
5 | 5 | US-022 | As dev, I want Python FastAPI (server.py + features.py 20 routes, _serialize_turn) and Streamlit app (src/ui/app.py 5 pages) | MUST HAVE | US-021 | Backend Team | 3- Completed
5 | 5 | US-023 | As agent, I want React frontend (Vite 5 + Tailwind + react-router 6, framer-motion, query) with Landing/Login/Dashboard (Signals/KB/Reply/Risk)/Setup/Reports/Analytics/Knowledge/HallOfFame/Jira | MUST HAVE | US-021 | Frontend Team | 3- Completed
5 | 5 | US-024 | As user, I want API integration (api.js bearer), session/start, chat/message -> coachTurn, autopilot, manager-takeover, chat/end -> email report | MUST HAVE | US-023 | Frontend Team | 3- Completed
5 | 5 | US-025 | As power user, I want Feature Lab (Multiverse/Tone/Compliance/Jira), TTS fallback, Survival, analytics and jsPDF export | SHOULD HAVE | US-023 | Frontend Team | 3- Completed
6 | 6 | US-026 | As QA, I want tests: pytest 14 + load, vitest 7, node --test, CI on push | MUST HAVE | US-022 | QA Team | 3- Completed
6 | 6 | US-027 | As DevOps, I want deploy: Vercel (frontend+backend), Streamlit Cloud, Neon Postgres, /health (engine/RAG/db) | MUST HAVE | US-021 | DevOps | 3- Completed
6 | 6 | US-028 | As stakeholder, I want docs: 10-slide PPT exactly, KT Guide + Q&A Bank 25 Qs, HTML docs, Deep Dive, CheatSheet | MUST HAVE | No Dependency | Team Lead | 3- Completed
6 | 6 | US-029 | As QA, I want hardening: ephemeral FS fix (DB authoritative), two-backends-one-Vercel guard, all agents fallback, load test | MUST HAVE | US-026 | QA Team | 3- Completed
6 | 6 | US-030 | As PM, I want final packaging: templates filled, GitHub release final/main, 5-min demo script, submit 28-Aug-2026 | MUST HAVE | US-028 | Team Lead | 3- Completed
Note: 30 user stories across 6 sprints (Agile Template v0.1). MoSCoW applied. All 3-Completed for 28-Aug-2026 submission. Reference files Sample_Agile.xls and Agile_Template.xlsm NOT uploaded/edited - this file is the completed submission for CoachAI (github.com/MasterJi27).

## Sprint Backlog
CoachAI - Sprint Backlog (Task Breakdown, 6 Sprints)
Sprint-wise tasks with effort (hrs), owner and acceptance criteria -> maps US-IDs to executable tasks
Sprint | Task ID | US ID | Task / Activity | Assignee | Est. Hrs | Actual Hrs | Dependency | Status
1 | T-01 | US-001 | Requirement workshop, Infosys problem analysis, MVP scope and acceptance criteria | Team Lead/BA | 8 | 8 | - | 3- Completed
1 | T-02 | US-002 | Init GitHub repo, .gitignore, branch main, MIT license, README structure | Team Lead | 4 | 4 | T-01 | 3- Completed
1 | T-03 | US-003 | Draw architecture (React-Node-Python-Postgres-LLM) and 9-step flow, document in KT guide | AI Architect | 6 | 6 | T-01 | 3- Completed
1 | T-04 | US-004 | Create .env.example (15 keys), config.py with 3-layer fallback (settings->env->st.secrets) | Backend Team | 5 | 5 | T-02 | 3- Completed
1 | T-05 | US-005 | Code Orchestrator singleton + ConversationManager (rehydrate via full_state JSON) | AI Team | 10 | 10 | T-03 | 3- Completed
2 | T-06 | US-006 | Build customer_simulator: 6 fallbacks, Hinglish mixer, sentiment machine, <=140 chars | AI Team | 8 | 8 | T-05 | 3- Completed
2 | T-07 | US-007 | Build intent_sentiment: builder, temp 0.1, JSON regex, frustration/trend heuristics | AI Team | 8 | 8 | T-05 | 3- Completed
2 | T-08 | US-008 | Build escalation_monitor weighted formula + 6 unit tests | AI Team | 6 | 5 | T-07 | 3- Completed
2 | T-09 | US-009 | Build coaching_suggestion: macros inject, tone/clarity + LLM, STAY15 logic | AI Team | 8 | 8 | T-07 | 3- Completed
2 | T-10 | US-010 | Build post_interaction_summary scoring + report JSON | AI Team | 6 | 6 | T-09 | 3- Completed
3 | T-11 | US-011 | Implement ingest.py: 7 formats, para->512 chunks, sentence re-split | AI Team | 8 | 8 | T-01 | 3- Completed
3 | T-12 | US-012 | Implement hybrid search: embed cosine, BM25 fallback, JSONB cache | AI Team | 10 | 10 | T-11 | 3- Completed
3 | T-13 | US-013 | Build knowledge_recommendation + gap <0.45 + auto_kb draft | AI Team | 7 | 7 | T-12 | 3- Completed
3 | T-14 | US-014 | Build deep_analysis 1-call (CSAT/churn/viral/PR/fraud/defection/mind-read) | AI Team | 9 | 9 | T-07 | 3- Completed
3 | T-15 | US-015 | Build predictive_csat, defection, viral, fraud (keyword pre-scan -> LLM) | AI Team | 8 | 8 | T-14 | 3- Completed
4 | T-16 | US-016 | Build mind_reader, multiverse (3 branches), cognitive, patience, bot menu | AI Team | 10 | 10 | T-14 | 3- Completed
4 | T-17 | US-017 | Build manager_supervisor (>=0.5 no-op), compliance, tone_rewriter (<10 guard), auto_pilot | AI Team | 10 | 10 | T-09 | 3- Completed
4 | T-18 | US-018 | Build jira_bug_generator, scenario_generator, qa_audit (21 checks, pass >=0.75) | AI Team | 8 | 8 | T-10 | 3- Completed
4 | T-19 | US-019 | Implement mock_backend (Rs.500 guard) + composio_backend graceful fail | Backend Team | 7 | 7 | T-18 | 3- Completed
4 | T-20 | US-020 | Build survival_game (4 tickets, 0.85/0.6/0.35, shield@3, +500) + hall_of_fame | AI Team | 6 | 6 | T-10 | 3- Completed
5 | T-21 | US-021 | Build Node Express backend: auth, sessionStore pg rehydration, 40+ routes | Backend Team | 14 | 14 | T-05 | 3- Completed
5 | T-22 | US-022 | Build Python FastAPI (server+features 20 routes, _serialize_turn) + Streamlit | Backend Team | 10 | 10 | T-21 | 3- Completed
5 | T-23 | US-023 | Build React frontend (Vite+Tailwind, 10 pages, 58% code-split) dark navy glassmorphism | Frontend Team | 16 | 16 | T-21 | 3- Completed
5 | T-24 | US-024 | Integrate frontend-backend: Login/guest, Setup->Dashboard 4-tab, Autopilot, takeover, end email | Frontend Team | 10 | 10 | T-23 | 3- Completed
5 | T-25 | US-025 | Build Feature Lab, Analytics, Reports jsPDF, Knowledge admin tabs | Frontend Team | 8 | 8 | T-24 | 3- Completed
6 | T-26 | US-026 | Write tests: pytest 14 + load, vitest 7, node --test | QA Team | 8 | 8 | T-22 | 3- Completed
6 | T-27 | US-027 | Deploy: Vercel (frontend+backend), Streamlit Cloud, Neon Postgres, /health | DevOps | 8 | 7 | T-21 | 3- Completed
6 | T-28 | US-028 | Create docs: PPT 10 slides exactly, KT Guide 342 lines, HTML docs, Deep Dive, QA Bank 25 Qs | Team Lead | 10 | 10 | - | 3- Completed
6 | T-29 | US-029 | Hardening: two-backends guard, ephemeral FS -> DB, all fallbacks, load test | QA Team | 6 | 6 | T-26 | 3- Completed
6 | T-30 | US-030 | Package: fill Agile/Defect/UTP, GitHub push final/main, rehearse 10min demo, submit 28-Aug | Team Lead | 4 | 4 | T-28 | 3- Completed

## Stand up Meeting
CoachAI - Daily Stand-up Log (Jun-Aug 2026, 6 Sprints)
Daily 15-min stand-ups: Yesterday / Today / Blockers - Scrum Master: Team Lead ¦ 10:00 AM IST ¦ Google Meet + GitHub Projects
Date | Sprint | Team Member | What was done yesterday? | What will be done today? | Blockers / Impediments | Action Items
2026-07-07 | Sprint 1 | Team Lead | Kick-off, requirement analysis, created GitHub repo and README skeleton | Finalize architecture diagram and per-turn flow, create .env.example | None | Review architecture by EOD
2026-07-08 | Sprint 1 | AI Team | Implemented config.py with 3-layer key fallback, graceful degradation tested | Start Orchestrator singleton and ConversationManager skeleton | Azure key not yet provisioned - using Groq fallback | Request Azure OpenAI access
2026-07-10 | Sprint 1 | Backend Team | Completed Orchestrator lifecycle and DB schema (sessions full_state JSON) | Wire Streamlit sidebar and setup page | None | Demo Sprint 1 review 11-Jul
2026-07-14 | Sprint 2 | AI Team | Built customer_simulator (Hinglish, sentiment) + intent_sentiment (JSON regex fallback) | Build escalation_monitor weighted formula + unit tests | LLM returns markdown fence - added regex extractor | Refine prompt for JSON-only
2026-07-15 | Sprint 2 | AI Team | Escalation monitor done, coaching_suggestion with macros inject working | Implement post_interaction_summary scoring and report JSON | Clarity score variance high - tuning heuristics | Add fallback for clarity
2026-07-18 | Sprint 2 | AI Team | Sprint 2 review: 5/5 US done, demo <0.5s pipeline | Begin Sprint 3: RAG ingestion multi-format | None | Sprint 3 planning
2026-07-21 | Sprint 3 | AI Team | Ingest .txt/.pdf via PyPDF2, 512-char chunks, 19 FAQs loaded | Build hybrid retrieval (embedding + BM25) and JSONB cache | OpenRouter 429 - keyword fallback saved demo | Add retry + fallback log
2026-07-23 | Sprint 3 | AI Team | Knowledge recommendation + KB-gap <0.45 done, auto-KB draft to pending/ | Implement deep_analysis one-call and 4 risk agents | Deep prompt too long - compress but keep single call | Compress prompt, keep JSON contract
2026-07-25 | Sprint 3 | AI Team | Deep signals working, CSAT vs heuristic verified | Test RAG on 30 queries, tune 0.45 threshold | None | Sprint 3 demo 26-Jul
2026-07-28 | Sprint 4 | AI Team | Built mind_reader, multiverse, cognitive_load, patience_clock, bot Agent menu | Implement manager_supervisor (0.5), compliance, tone rewriter | Manager whisper too frequent - raised to 0.5 | Adjust threshold, add hysteresis
2026-07-30 | Sprint 4 | AI Team | Tone rewriter <10 guard done, auto_pilot + Composio mock working | Build Jira generator, scenario generator, QA audit (21 checks) | Composio SDK breaking change 0.18->0.19 | Pin deps to 0.18.1
2026-08-01 | Sprint 4 | Backend Team | Survival arcade and Hall of Fame done, power-ups tested | Sprint 4 review, start Node backend auth and sessionStore | Survival singleton shared - known limitation | Document in gotchas
2026-08-04 | Sprint 5 | Backend Team | Node Express backend: auth (register/login/guest), pg rehydration, 20 routes, health | Build React frontend shell (Landing/Login/Dashboard) and bearer wrapper | Two backends same Vercel project - deploy order careful | Deploy Node first, verify /api/auth/me
2026-08-06 | Sprint 5 | Frontend Team | Dashboard 4-tab rail (Signals/KB/Reply/Risk) wired to /api/chat/message | Implement Feature Lab, Analytics, Reports, Knowledge admin | Risk tab overflow on mobile - fixed Tailwind | Test responsive at 360px
2026-08-08 | Sprint 5 | Frontend Team | Feature Lab (Multiverse/Tone/Compliance/Jira) + autopilot/takeover done | End-to-end guest->Setup->Dashboard->Report->Email test | DB rehydration on cold start verified | Add activity log
2026-08-11 | Sprint 6 | QA Team | pytest 14 tests + vitest 7 + node --test all green locally | Deploy to Vercel prod and Streamlit Cloud, configure DATABASE_URL | Ephemeral FS caused missing reports - switched to DB | Never read from fs on Vercel
2026-08-13 | Sprint 6 | Team Lead | Drafted PPT 10 slides exactly, KT Guide + Deep Dive, HTML docs | Create QA Bank 25 Qs, CheatSheet, File Structure PDFs | PPT had 12 slides - trimmed to 10 | Enforce 10-slide rule
2026-08-15 | Sprint 6 | QA Team | Load test 50 concurrent, p95 <0.8s, fallback chain reliable (Azure->Groq) | Fill Agile/Defect/UTP templates, final push to final/main | .gitignore ignored Doc PDFs - fixed with !Doc/**/*.pdf | Verify git status PDFs tracked
2026-08-27 | Sprint 6 | Team Lead | Completed templates, final review, 10min + 5min Q&A dry-run | Submit to Classroom and GitHub by 28-Aug | None - submission ready | Upload and verify

## Retrospection
CoachAI - Sprint Retrospectives (6 Sprints)
What went well / What went wrong / Improvements - reviewed at each sprint review
Sprint (Dates) | What Went Well | What Went Wrong / Challenges | Action Items / Improvements | Owner | Due Date / Status
Sprint 1 07-12 Jul 2026 | Clear architecture and 9-step flow saved rework; Graceful degradation prevented late surprises; GitHub branching clean | Azure access delayed - started with Groq; Initial chunk 1024 too large, truncated tips | Request Azure key early; reduce chunk to 512 and sentence re-split; document 3-layer fallback | Team Lead AI Architect | 12-Jul Done
Sprint 2 14-19 Jul 2026 | <0.5s pipeline with ThreadPool 2 workers; Escalation formula easy to tune and test; Macros library made suggestions product-specific | LLM JSON failed when model added ```json fences; Clarity score variance across intents | Add regex JSON extractor + heuristic fallback for every agent; Tune coaching prompt with valid intents enum | AI Team QA Team | 19-Jul Done
Sprint 3 21-26 Jul 2026 | Hybrid RAG (semantic+BM25) works offline; KB-gap <0.45 + auto-KB draft delighted reviewers; Deep one-call cut latency 40% | OpenRouter 429 during demo; Viral/fraud keyword false negatives on Hinglish | Add retry + keyword seeded defaults + log; Expand Hinglish lists, tests for 'paise wapas' | AI Team | 26-Jul Done
Sprint 4 28 Jul-02 Aug | 25 agents single responsibility - prompts small/testable; Composio real actions + mock offline; Survival and Hall of Fame wow factor | Composio SDK breaking change 0.18->0.19; Manager whisper fired too often (>0.3); Survival singleton shared | Pin composio>=0.18.1,<0.20; Raise threshold to >=0.5 + hysteresis; Document singleton limit in gotchas | AI Team Backend Team | 02-Aug Done
Sprint 5 04-09 Aug 2026 | Node backend mirrors Python - frontend auth works (/api/auth/*); React 4-tab rail highly usable; Feature Lab strong demo | Two backends same Vercel project confusion; Risk tab overflow mobile; DB rehydration edge: cold instance lost _sessions | Deploy Node to coachai-backend, verify /health before frontend; Fix responsive; Add JSON rehydrate via full_state + activity log | Frontend Team Backend Team | 09-Aug Done
Sprint 6 11-27 Aug 2026 | Full suite green (pytest+vitest+node), p95 <0.8s; 10-slide PPT exactly + KT Guide + QA Bank ready; Ephemeral FS fix closed top bug | PPT initially 12 slides - had to trim; .gitignore ignored Doc PDFs - almost missed; Template filling took full day | Enforce slide count checklist; Add !Doc/**/*.pdf; Create generator script for next batch; Dry-run 27-Aug, submit 28-Aug | Team Lead QA Team All | 27-Aug Done
Outcome: 30/30 user stories completed, 0 blockers pending, velocity ~5 stories/sprint. Top risks mitigated: two-backends-one-Vercel and ephemeral FS via pg JSONB rehydration and DB-authoritative reads. Next: unify to single canonical backend, add pgvector at scale.